# PLAN OF ACTION & MILESTONES (POA&M)

Version: 2.3 Date: February 11, 2026 Organization: The Contract Coach System: CyberHygiene Production Network (cyberinabox.net) Reference: System Security Plan Version 2.0 Classification: Controlled Unclassified Information (CUI)

## Executive Summary

SPRS Score Status: - Current Score: 88/110 (80.0%) - Target Score: 110/110 (100%) - Target Completion: March 31, 2026 (most items), June 30, 2026 (IR testing)

SPRS score revised per independent CMMC L2 Preliminary Gap Analysis (February 9, 2026). See Assessment Reference section below.

## Assessment Reference

Document: CMMC Level 2 Preliminary Gap Analysis Assessment Date: February 9, 2026 Assessor: Independent C3PAO Preliminary Reviewer Methodology: CMMC Assessment Guide Level 2, Version 2.13 (September 2024) Reference Standard: NIST SP 800-171 Rev 2 / 32 CFR 170.16 / 32 CFR 170.17

### Variance Summary

The independent assessment identified a 19-point SPRS variance between the self-assessed score (107/110) and the independent score (88/110). The self-assessment has been corrected to align with the independent findings.

| Gap Category | Self-Assessment | Independent Assessment | Variance |
| --- | --- | --- | --- |
| MFA (3.5.3) | -3 | -5 | -2 |
| IR Testing (3.6.3) | -0.5 | -1 | -0.5 |
| Training (3.2.1, 3.2.2, 3.2.3) | 0 | -7 | -7 |
| Risk Assessment (3.11.1) | 0 | -3 | -3 |
| Security Assessment (3.12.1) | 0 | -3 | -3 |
| Session Lock (3.1.10) | 0 | -1 | -1 |
| Login Banners (3.1.9) | 0 | -1 | -1 |
| Removable Media (3.8.7) | 0 | -1 | -1 |
| Total | -3.5 | -22 | -18.5 |

Root Causes of Variance: 1. DRAFT policies credited as MET (CMMC Guide v2.13 requires formally approved policies) 2. Planned implementations credited as MET (USBGuard, training, risk assessment) 3. MFA weight scored at -3 (IA-8 only) instead of -5 (full 3.5.3 weight) 4. Several NOT MET items not captured as SPRS deficits in POA&M

## POA&M Summary

| Metric | Count | Percentage |
| --- | --- | --- |
| Total Items | 45 | 100% |
| Completed | 26 | 58% |
| On Track | 14 | 31% |
| Ongoing | 2 | 4% |
| Closed (Risk Accepted) | 1 | 2% |
| Planned | 2 | 4% |

Priority Distribution (items with assigned priority): - High Priority: 9 items - Medium Priority: 15 items - Low Priority: 4 items

## Section 1: COMPLETED POA&M Items

Items completed and verified as of February 3, 2026:

### Infrastructure and Technical Controls

| POA&M ID | Weakness/Deficiency | NIST Controls | Completion Date | Evidence | Status |
| --- | --- | --- | --- | --- | --- |
| POA&M-001 | Samba file sharing not operational | AC-3, AC-6, AU-2 | 01/26/2026 | Samba share operational at /srv/samba/shared, FreeIPA integration verified | COMPLETED |
| POA&M-002 | Email server not deployed | SC-8, SC-13, SI-3 | 01/26/2026 | Postfix 3.5.25 and Dovecot 2.3.16 operational with TLS encryption | COMPLETED |
| POA&M-003 | Backup system not implemented | CP-9, CP-10 | 10/28/2025 | ReaR backup system operational with weekly full backups and daily incremental backups | COMPLETED |
| POA&M-008 | IDS/IPS not operational on firewall | SI-4 | 10/28/2025 | Wazuh SIEM v4.9.2 deployed with Suricata integration on pfSense | COMPLETED |
| POA&M-009 | File integrity monitoring not deployed | SI-7 | 10/28/2025 | Wazuh FIM operational with 12-hour scan intervals on critical paths | COMPLETED |
| POA&M-010 | SSL certificate not installed | SC-8, SC-13 | 01/26/2026 | SSL.com wildcard certificate deployed, valid until October 28, 2026 | COMPLETED |

### Policy Documentation

| POA&M ID | Weakness/Deficiency | NIST Controls | Completion Date | Evidence | Status |
| --- | --- | --- | --- | --- | --- |
| POA&M-015 | Incident Response Policy not documented | IR-1, IR-4, IR-6, IR-8 | 11/02/2025 | TCC-IRP-001 approved and effective | COMPLETED |
| POA&M-016 | Incident Response Procedures not documented | IR-2 through IR-8 | 11/02/2025 | Complete IR procedures in TCC-IRP-001 | COMPLETED |
| POA&M-017 | Personnel screening not documented | PS-3 | 11/02/2025 | TCC-PS-001, Section 2.3 documents TS clearance | COMPLETED |
| POA&M-018 | Personnel Security Policy not developed | PS-1 through PS-8 | 11/02/2025 | TCC-PS-001 approved and effective | COMPLETED |
| POA&M-019 | Physical security controls not documented | PE-1 through PE-20 | 11/02/2025 | TCC-PE-MP-001 Part 1 approved | COMPLETED |
| POA&M-020 | Media protection procedures not developed | MP-1 through MP-8 | 11/02/2025 | TCC-PE-MP-001 Part 2 approved | COMPLETED |
| POA&M-021 | Media sanitization not documented | MP-6 | 11/02/2025 | TCC-PE-MP-001, Section 2.6 (LUKS erase, shred) | COMPLETED |
| POA&M-022 | Risk Assessment Policy not developed | RA-1, RA-2, RA-3, RA-7 | 11/02/2025 | TCC-RA-001 approved and effective | COMPLETED |
| POA&M-023 | Vulnerability scanning not documented | RA-5 | 11/02/2025 | TCC-RA-001, Section 2.5 (Wazuh, OpenSCAP) | COMPLETED |
| POA&M-024 | System Integrity Policy not developed | SI-1, SI-2, SI-4 through SI-12 | 11/02/2025 | TCC-SI-001 approved and effective | COMPLETED |
| POA&M-025 | Malware protection not documented | SI-3 | 11/02/2025 | TCC-SI-001, Section 2.3 (YARA, Wazuh FIM) | COMPLETED |
| POA&M-026 | Acceptable Use Policy not developed | AC-1, PS-6, PL-4 | 11/02/2025 | TCC-AUP-001 approved and effective | COMPLETED |
| POA&M-027 | Risk Management Framework not established | RA-3, RA-5, RA-7 | 11/02/2025 | TCC-RA-001 with NIST SP 800-30 methodology | COMPLETED |

### AI Security Controls (NEW - February 2026)

| POA&M ID | Weakness/Deficiency | NIST Controls | Completion Date | Evidence | Status |
| --- | --- | --- | --- | --- | --- |
| POA&M-036 | AI Gateway Security Controls | 3.1.1, 3.1.2, 3.5.2 | 02/02/2026 | OpenClaw gateway with token auth, loopback-only binding, tool allowlist | COMPLETED |
| POA&M-037 | Prompt Injection Defense (Citadel Guard) | 3.13.1, 3.6.1 | 02/02/2026 | Citadel Guard with 20+ detection patterns, sanitize-and-flag action | COMPLETED |
| POA&M-038 | Human-in-the-Loop Enforcement | 3.1.5, 3.1.7, 3.5.2 | 02/02/2026 | Sudo approval proxy with HMAC-signed responses, 120s timeout | COMPLETED |
| POA&M-039 | AI Audit Logging | 3.3.1, 3.3.2 | 02/02/2026 | Comprehensive logging at gateway, proxy, and agent layers | COMPLETED |
| POA&M-040 | AI Network Confinement | 3.1.7, 3.13.1, 3.13.8 | 02/02/2026 | nftables egress rules, UID-based filtering for openclaw-svc | COMPLETED |
| POA&M-041 | AI Security Documentation | 3.4.1, 3.4.5 | 02/02/2026 | OPENCLAW_AI_SECURITY_ARCHITECTURE.md, SBOM.json, SSP addendum | COMPLETED |
| POA&M-SPRS-3 | Email spam protection (SI-8) | SI-8 | 02/03/2026 | OpenDKIM 2.11.0, SpamAssassin 3.4.6, spamass-milter operational | COMPLETED |

## Section 2: CLOSED POA&M Items (Risk Accepted)

| POA&M ID | Weakness/Deficiency | NIST Controls | Status | Risk Acceptance Reference |
| --- | --- | --- | --- | --- |
| POA&M-014 | ClamAV antivirus FIPS incompatible | SI-3 | CLOSED - Risk Accepted | Risk_Acceptance_ClamAV_FIPS_Incompatibility.md |

Risk Acceptance Details: - ClamAV 1.4.3 incompatible with FIPS mode due to OpenSSL 3 cryptographic restrictions - Compensating controls: YARA 4.5.2 pattern detection (operational), Wazuh FIM, network IDS/IPS - Risk level: LOW (with compensating controls) - Annual review scheduled: December 31, 2026

## Section 2A: CONSOLIDATED POA&M Items

| POA&M ID | Original Weakness | Consolidated Into | Rationale | Date |
| --- | --- | --- | --- | --- |
| POA&M-SPRS-1 | MFA not implemented for non-organizational users (IA-8) | POA&M-004 | Same FreeIPA OTP deployment covers both organizational and non-organizational users. IA-8 requirement addressed by the same MFA implementation as 3.5.3. | 02/11/2026 |

## Section 3: ON TRACK POA&M Items

### Immediate Priority (Target: March 15, 2026)

| POA&M ID | Weakness/Deficiency | NIST Controls | SPRS Impact | Target Date | Priority | Status | POC |
| --- | --- | --- | --- | --- | --- | --- | --- |
| POA&M-029 | Session lock not configured (15-min timeout) | 3.1.10 (AC-11) | -1 point | 03/15/2026 | High | ON TRACK | Shannon |
| POA&M-034 | Login banners not implemented on all systems | 3.1.9 (AC-8) | -1 point | 03/15/2026 | Low | ON TRACK | Shannon |

POA&M-029 Assessment Finding: Independent assessment confirms 3.1.10 NOT MET. Policy exists (TCC-AUP-001 Section 2.3) but technical implementation incomplete. Configure GNOME/KDE screen lock at 15 minutes on all workstations.

POA&M-034 Assessment Finding: Independent assessment confirms 3.1.9 NOT MET. Configure /etc/issue, /etc/issue.net, and SSH Banner directive on all systems.

### Q1 End (Target: March 31, 2026)

| POA&M ID | Weakness/Deficiency | NIST Controls | SPRS Impact | Target Date | Priority | Status | POC |
| --- | --- | --- | --- | --- | --- | --- | --- |
| POA&M-004 | Multi-factor authentication not configured | 3.5.3 (IA-2(1), IA-2(2)) | -5 points | 03/31/2026 | High | ON TRACK | Shannon |
| POA&M-006 | Security awareness training program not implemented | 3.2.1 (AT-2, AT-3) | -3 points | 03/31/2026 | Medium | ON TRACK | Shannon |
| POA&M-011 | Security control assessment not formally established | 3.12.1 (CA-2) | -3 points | 03/31/2026 | Medium | ON TRACK | Shannon |
| POA&M-030 | Audit & Accountability Policy not developed | AU-1 through AU-12 | — | 03/31/2026 | High | ON TRACK | Shannon |
| POA&M-031 | Configuration Management Policy not developed | CM-1 through CM-11 | — | 03/31/2026 | Medium | ON TRACK | Shannon |
| POA&M-032 | Security Awareness and Training Policy not developed | 3.2.2, 3.2.3 (AT-1 through AT-4) | -4 points | 03/31/2026 | Medium | ON TRACK | Shannon |
| POA&M-033 | Identification and Authentication Policy not developed | IA-1 through IA-11 | — | 03/31/2026 | Medium | ON TRACK | Shannon |
| POA&M-044 | Removable media technical enforcement (USBGuard) | 3.8.7 (MP.L2-3.8.7) | -1 point | 03/31/2026 | Medium | ON TRACK | Shannon |
| POA&M-045 | System & Communications Protection Policy not developed | SC-1 through SC-16 | — | 03/31/2026 | Medium | ON TRACK | Shannon |

POA&M-004 (MFA) Assessment Finding: Independent assessment scores 3.5.3 at full -5 point weight (not -3 as previously assessed for IA-8 only). FreeIPA natively supports OTP tokens; remediation is straightforward. This item now absorbs POA&M-SPRS-1 (IA-8 for non-organizational users) — the same FreeIPA OTP deployment covers both organizational and non-organizational user MFA requirements.

POA&M-006 (Security Awareness Training) Assessment Finding: Independent assessment identifies 3.2.1 (Role-Based Risk Awareness) as NOT MET with -3 point deficit. AUP acknowledgment does not constitute role-based training per CMMC Guide v2.13. Must establish a formal security awareness training program with documented completion records.

POA&M-011 (Security Control Assessment) Assessment Finding: Independent assessment identifies 3.12.1 as NOT MET with -3 point deficit. Scope broadened from SSP quarterly review to comprehensive security control assessment covering all 110 NIST 800-171 requirements. Must include formal assessment per NIST SP 800-53A methodology. Note: the February 9, 2026 preliminary gap analysis itself contributes toward satisfying 3.12.1.

POA&M-032 (AT Policy) Assessment Finding: Independent assessment identifies 3.2.2 (Role-Based Training, -3) and 3.2.3 (Insider Threat Awareness, -1) as NOT MET, combined -4 point deficit. Policy must include insider threat awareness training component. TCC-AT-001 currently in DRAFT status; must be formally approved and initial training conducted and documented.

POA&M-044 (Removable Media — NEW): Independent assessment identifies 3.8.7 as NOT MET with -1 point deficit. Policy exists (TCC-PE-MP-001 Section 2.7) but no technical enforcement mechanism. Deploy USBGuard on all systems, create device whitelist for authorized USB storage, configure Wazuh monitoring for USBGuard events.

POA&M-045 (SC Policy — NEW): Finalize TCC-SC-001 (currently PLANNED status). Assessment notes 5 of 11 policy families lack approved documentation. SC is the only family with no draft started. SPRS impact: 0 (maturity improvement — all SC controls technically MET). All 16 SC requirements scored MET by independent assessment.

### Q2 (Target: April 30, 2026)

| POA&M ID | Weakness/Deficiency | NIST Controls | SPRS Impact | Target Date | Priority | Status | POC |
| --- | --- | --- | --- | --- | --- | --- | --- |
| POA&M-012 | Disaster recovery testing not performed | CP-4 | — | 04/30/2026 | High | ON TRACK | Shannon |
| POA&M-035 | First annual risk assessment not conducted | 3.11.1 (RA-3) | -3 points | 04/30/2026 | High | ON TRACK | Shannon |

POA&M-035 (Risk Assessment) Assessment Finding: Independent assessment identifies 3.11.1 as NOT MET with -3 point deficit. Risk Management Policy (TCC-RA-001) is approved with NIST SP 800-30 methodology established, but the first formal periodic risk assessment has not been conducted. Risk identification through POA&M and Wazuh monitoring does not substitute for a formal risk assessment.

### Q2 End (Target: June 30, 2026)

| POA&M ID | Weakness/Deficiency | NIST Controls | SPRS Impact | Target Date | Priority | Status | POC |
| --- | --- | --- | --- | --- | --- | --- | --- |
| POA&M-SPRS-2 | IR tabletop exercise not conducted | 3.6.3 (IR-3) | -1 point | 06/30/2026 | Medium | ON TRACK | Shannon |

POA&M-SPRS-2 (IR Testing) Assessment Finding: Independent assessment scores 3.6.3 at -1 point (updated from -0.5 per assessment weight). Annual tabletop exercise requirement documented in TCC-IRP-001 but first exercise not yet performed.

## Section 4: ONGOING POA&M Items

| POA&M ID | Weakness/Deficiency | NIST Controls | Frequency | Status | POC |
| --- | --- | --- | --- | --- | --- |
| POA&M-042 | AI Continuous Monitoring | 3.3.4, 3.6.1, 3.12.3 | Daily/Weekly/Monthly | ONGOING | Shannon |
| POA&M-043 | Citadel Guard Pattern Updates | 3.14.1, 3.14.6 | Quarterly | ONGOING | Shannon |

POA&M-042 Milestones: - Daily: Citadel Guard log review - Weekly: Approval request analysis - Monthly: HITL flow testing - Quarterly: Penetration testing

POA&M-043 Milestones: - Q1 2026: Review emerging injection techniques - Q1 2026: Update pattern database - Q1 2026: Test against new payloads

## Section 5: PLANNED POA&M Items

| POA&M ID | Weakness/Deficiency | NIST Controls | Target Date | Priority | Status | POC |
| --- | --- | --- | --- | --- | --- | --- |
| POA&M-013 | Wazuh Dashboard deployment | SI-4 (enhancement) | 06/30/2026 | Low | PLANNED | Shannon |
| POA&M-028 | VPN with MFA for remote access | AC-17, IA-2(1) | 06/30/2026 | High | PLANNED | Shannon |

## POA&M Metrics

### By Status

| Status | Count | Percentage |
| --- | --- | --- |
| Completed | 26 | 58% |
| On Track | 14 | 31% |
| Ongoing | 2 | 4% |
| Closed (Risk Accepted) | 1 | 2% |
| Planned | 2 | 4% |

### By Priority

| Priority | Total | Completed | On Track | Ongoing | Planned/Closed |
| --- | --- | --- | --- | --- | --- |
| High | 9 | 3 | 5 | 0 | 1 |
| Medium | 15 | 7 | 8 | 0 | 0 |
| Low | 4 | 2 | 1 | 0 | 1 |
| Ongoing | 2 | 0 | 0 | 2 | 0 |

### By Target Date

| Quarter | Target Items | Notes |
| --- | --- | --- |
| Q1 2026 (Jan-Mar) | 11 items | Immediate focus: MFA, training, session lock, banners, USBGuard, policies |
| Q2 2026 (Apr-Jun) | 5 items | IR testing, risk assessment, DR testing, VPN, Wazuh dashboard |

### By Control Family

| Family | Total Items | Completed | Open | SPRS Deficit |
| --- | --- | --- | --- | --- |
| Access Control (AC) | 5 | 2 | 3 | -2 |
| Awareness & Training (AT) | 2 | 0 | 2 | -7 |
| Audit & Accountability (AU) | 1 | 0 | 1 | — |
| Security Assessment (CA) | 1 | 0 | 1 | -3 |
| Configuration Management (CM) | 1 | 0 | 1 | — |
| Contingency Planning (CP) | 2 | 1 | 1 | — |
| Identification & Authentication (IA) | 2 | 0 | 2 | -5 |
| Incident Response (IR) | 3 | 2 | 1 | -1 |
| Media Protection (MP) | 3 | 2 | 1 | -1 |
| Physical Protection (PE) | 1 | 1 | 0 | — |
| Personnel Security (PS) | 2 | 2 | 0 | — |
| Risk Assessment (RA) | 4 | 3 | 1 | -3 |
| System & Communications Protection (SC) | 3 | 2 | 1 | — |
| System & Information Integrity (SI) | 7 | 5 | 2 | — |
| AI Security Controls | 8 | 6 | 2 | — |

Items assigned to primary control family. Total: 45 items, 26 completed, 19 open. SPRS deficit: -22.

## Completion Trend

| Date | Total Items | Completed | % Complete | Notes |
| --- | --- | --- | --- | --- |
| 10/26/2025 | 14 | 0 | 0% | Initial POA&M |
| 10/28/2025 | 14 | 3 | 21% | Backup, IDS/IPS, FIM complete |
| 10/31/2025 | 14 | 3 | 21% | POA&M-014 advanced to 85% |
| 11/02/2025 | 28 | 16 | 57% | Policy documentation complete |
| 12/26/2025 | 31 | 16 | 52% | SPRS gaps added |
| 01/26/2026 | 31 | 19 | 61% | Samba, Email, SSL complete |
| 02/03/2026 | 43 | 26 | 60% | AI controls integrated, POA&M-014 closed, POA&M-SPRS-3 complete |
| 02/11/2026 | 45 | 26 | 58% | v2.3: Reconciled with independent assessment. SPRS revised 107→88. Added POA&M-044, 045. Consolidated SPRS-1 into 004. |
| Projected 03/31/2026 | 45 | 37+ | 82%+ | Q1 2026 targets |
| Projected 06/30/2026 | 45 | 40+ | 89%+ | Most items complete |

## SPRS Impact Summary

### Current Deficits (per Independent Assessment, February 9, 2026)

| POA&M ID | Req ID | Control Description | Weight | Target Date | Status |
| --- | --- | --- | --- | --- | --- |
| POA&M-004 | 3.5.3 | Multifactor Authentication | -5 | 03/31/2026 | On Track |
| POA&M-006 | 3.2.1 | Role-Based Risk Awareness | -3 | 03/31/2026 | On Track |
| POA&M-032 | 3.2.2 | Role-Based Training | -3 | 03/31/2026 | On Track |
| POA&M-032 | 3.2.3 | Insider Threat Awareness | -1 | 03/31/2026 | On Track |
| POA&M-035 | 3.11.1 | Periodic Risk Assessment | -3 | 04/30/2026 | On Track |
| POA&M-011 | 3.12.1 | Security Control Assessment | -3 | 03/31/2026 | On Track |
| POA&M-029 | 3.1.10 | Session Lock | -1 | 03/15/2026 | On Track |
| POA&M-034 | 3.1.9 | Login Banners | -1 | 03/15/2026 | On Track |
| POA&M-SPRS-2 | 3.6.3 | IR Testing | -1 | 06/30/2026 | On Track |
| POA&M-044 | 3.8.7 | Removable Media Enforcement | -1 | 03/31/2026 | On Track |
| TOTAL |  |  | -22 |  |  |

Current SPRS: 88/110 (80.0%) Target SPRS Upon Completion: 110/110 (100%)

### Previously Completed SPRS Items

| POA&M ID | Control | Points Recovered | Completion Date |
| --- | --- | --- | --- |
| POA&M-SPRS-3 | SI-8 (Spam Protection) | +2.0 | 02/03/2026 |

## Evidence Storage

All completed POA&M items have evidence stored in: - Policies: /home/dshannon/cyberhygiene-documentation/Certification and Compliance Evidence/Policies/ - Technical Documentation: /home/dshannon/cyberhygiene-documentation/ - Configuration Files: System configuration directories - AI Security Documentation: /data/ai-workspace/sysadmin-agent/docs/ - Compliance Reports: /backup/compliance-scans/ - Assessment Reports: /home/dshannon/CyberSecurity/Current/Assessments/

## Review Schedule

- Quarterly POA&M Review: January, April, July, October

- Next Review: April 30, 2026

- POA&M Owner: Donald E. Shannon, ISSO

## Document Control

Classification: Controlled Unclassified Information (CUI) Owner: Donald E. Shannon, ISSO Distribution: Owner/ISSO, Authorized Auditors, C3PAO Assessors

### Revision History

| Version | Date | Author | Description |
| --- | --- | --- | --- |
| 1.0 | 10/26/2025 | D. Shannon | Initial POA&M with 14 items |
| 1.1 | 10/28/2025 | D. Shannon | Marked POA&M-003, 008, 009 complete |
| 1.2 | 10/31/2025 | D. Shannon | POA&M-014 advanced to 85% |
| 1.3 | 11/02/2025 | D. Shannon | Unified POA&M: Marked 13 policy items complete, added 8 new items |
| 2.0 | 12/26/2025 | D. Shannon | Added 3 SPRS assessment gaps (POA&M-SPRS-1, SPRS-2, SPRS-3) |
| 2.1 | 12/26/2025 | D. Shannon | System verification: Completed POA&M-001 (Samba), POA&M-010 (SSL), POA&M-SPRS-3 (SpamAssassin). Updated POA&M-014 to Blocked |
| 2.2 | 02/03/2026 | D. Shannon | Major Update: SSP reference updated v1.9→v2.0. Integrated 8 AI POA&M items (POA&M-036 through POA&M-043). Closed POA&M-014 with risk acceptance. Rescheduled all overdue items. Updated POA&M-SPRS-3 status (OpenDKIM/SpamAssassin not functional). Completed POA&M-002 (Email operational). Total items: 31→43. Metrics recalculated. |
| 2.3 | 02/11/2026 | D. Shannon | Reconciled with independent CMMC L2 Preliminary Gap Analysis (02/09/2026). SPRS score revised from 107 to 88 per independent assessment. Added 10 SPRS deficit items. New: POA&M-044 (USBGuard), POA&M-045 (SC Policy). Consolidated POA&M-SPRS-1 into POA&M-004. Corrected item counts (v2.2 understated total by 1). Updated all metrics and control family assignments. |

END OF UNIFIED POA&M v2.3