# PLAN OF ACTION & MILESTONES (POA&M)

UPDATED: December 26, 2025 - Version 2.0 (Added 3 SPRS Gaps)

Organization: The Contract Coach System: CyberHygiene Production Network (cyberinabox.net) Date: December 26, 2025 Version: 1.4 Classification: Controlled Unclassified Information (CUI)

## POA&M Summary

Total Items: 31 Completed: 16 (57%) In Progress: 2 (7%) On Track: 8 (26%) Planned: 2 (7%)

High Priority Items: 3 Medium Priority Items: 7 Low Priority Items: 1

## Section 1: COMPLETED POA&M Items

Items completed as of December 26, 2025:

| POA&M ID | Weakness/Deficiency | NIST Controls | Completion Date | Evidence | Status |
| --- | --- | --- | --- | --- | --- |
| POA&M-003 | Backup system not implemented | CP-9, CP-10 | 10/28/2025 | ReaR backup system operational with weekly full backups and daily incremental backups. Documented in Backup_Procedures.docx | ✅ COMPLETED |
| POA&M-008 | IDS/IPS not operational on firewall | SI-4 | 10/28/2025 | Wazuh SIEM v4.9.2 deployed with Suricata integration on pfSense. Real-time monitoring and alerting operational. | ✅ COMPLETED (Exceeded) |
| POA&M-009 | File integrity monitoring not deployed | SI-7 | 10/28/2025 | Wazuh FIM operational with 12-hour scan intervals on critical paths (/etc, /boot, /var/ossec, /srv/samba) | ✅ COMPLETED |
| POA&M-015 | Incident Response Policy not documented | IR-1, IR-4, IR-6, IR-8 | 11/02/2025 | Incident Response Policy and Procedures (TCC-IRP-001) approved and effective | ✅ COMPLETED |
| POA&M-016 | Incident Response Procedures not documented | IR-2, IR-3, IR-4, IR-5, IR-6, IR-7, IR-8 | 11/02/2025 | Complete IR procedures documented in TCC-IRP-001, Section 2 | ✅ COMPLETED |
| POA&M-017 | Personnel screening not documented | PS-3 | 11/02/2025 | Personnel Security Policy (TCC-PS-001, Section 2.3) documents TS clearance exceeding CUI requirements | ✅ COMPLETED |
| POA&M-018 | Personnel Security Policy not developed | PS-1, PS-2, PS-4, PS-5, PS-6, PS-7, PS-8 | 11/02/2025 | Personnel Security Policy (TCC-PS-001) approved and effective | ✅ COMPLETED |
| POA&M-019 | Physical security controls not documented | PE-1 through PE-20 | 11/02/2025 | Physical and Media Protection Policy (TCC-PE-MP-001, Part 1) approved | ✅ COMPLETED |
| POA&M-020 | Media protection procedures not developed | MP-1 through MP-8 | 11/02/2025 | Physical and Media Protection Policy (TCC-PE-MP-001, Part 2) approved | ✅ COMPLETED |
| POA&M-021 | Media sanitization not documented | MP-6 | 11/02/2025 | Media sanitization procedures documented in TCC-PE-MP-001, Section 2.6 (LUKS erase, shred) | ✅ COMPLETED |
| POA&M-022 | Risk Assessment Policy not developed | RA-1, RA-2, RA-3, RA-7 | 11/02/2025 | Risk Management Policy and Procedures (TCC-RA-001) approved and effective | ✅ COMPLETED |
| POA&M-023 | Vulnerability scanning not documented | RA-5 | 11/02/2025 | Vulnerability management documented in TCC-RA-001, Section 2.5 (Wazuh continuous scanning, OpenSCAP quarterly) | ✅ COMPLETED |
| POA&M-024 | System Integrity Policy not developed | SI-1, SI-2, SI-4, SI-5, SI-6, SI-7, SI-10, SI-11, SI-12 | 11/02/2025 | System and Information Integrity Policy (TCC-SI-001) approved and effective | ✅ COMPLETED |
| POA&M-025 | Malware protection not documented | SI-3 | 11/02/2025 | Multi-layer malware protection documented in TCC-SI-001, Section 2.3 (ClamAV, YARA, Wazuh FIM, VirusTotal) | ✅ COMPLETED |
| POA&M-026 | Acceptable Use Policy not developed | AC-1, PS-6, PL-4 | 11/02/2025 | Acceptable Use Policy (TCC-AUP-001) approved and effective | ✅ COMPLETED |
| POA&M-027 | Risk Management Framework not established | RA-3, RA-5, RA-7 | 11/02/2025 | Complete risk management framework in TCC-RA-001 with NIST SP 800-30 methodology | ✅ COMPLETED |

## Section 2: IN PROGRESS POA&M Items

Items currently being worked on:

| POA&M ID | Weakness/Deficiency | NIST Controls | Resources Required | Target Date | Priority | Milestone/Task | Status | POC |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| POA&M-014 | Malware protection not fully FIPS-compliant. ClamAV incompatible with FIPS mode. Risk accepted with compensating controls. Reference: Risk_Acceptance_ClamAV_FIPS_Incompatibility.md | SI-3 | Multi-layered malware defense deployment | 12/31/2025 | Risk Accepted - See Risk Acceptance Memo | ⚠️ BLOCKED | 85% COMPLETE | Shannon |
| POA&M-005 | Formal Incident Response testing not conducted | IR-3 | Tabletop exercise planning and execution | 06/30/2026 | High | Annual IR tabletop exercise scheduled June 2026 per TCC-IRP-001. Exercise scenario development in Q1 2026. | SCHEDULED | Shannon |

## Section 3: ON TRACK POA&M Items

Items on schedule for completion:

| POA&M ID | Weakness/Deficiency | NIST Controls | Resources Required | Target Date | Priority | Milestone/Task | Status | POC |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| POA&M-002 | Email server not deployed | SC-8, SC-13, SI-3 | Postfix, Dovecot, Rspamd, ClamAV installation and configuration | 12/20/2025 | Medium | 1. Install packages2. Configure LDAP auth3. Enable encryption4. Test delivery5. Document | ON TRACK | Shannon |
| POA&M-004 | Multi-factor authentication not configured | IA-2(1), IA-2(2) | FreeIPA OTP or RADIUS integration | 12/22/2025 | Medium | 1. Configure OTP2. Test with users3. Document procedures4. Deploy to all systems | ON TRACK | Shannon |
| POA&M-006 | Security awareness training program not implemented | AT-2, AT-3 | Training materials and delivery method | 12/10/2025 | Medium | 1. Select training provider2. Schedule annual training3. Document completion4. Establish renewal cycle | ON TRACK | Shannon |
| POA&M-007 | USB device restrictions not enforced | AC-19, AC-20 | USBGuard installation and configuration | 03/31/2026 | Medium | 1. Install USBGuard2. Create whitelist3. Test restrictions4. Deploy to all systems | ON TRACK | Shannon |
| POA&M-011 | System Security Plan requires quarterly review process | CA-2 | Establish review schedule and checklist | 12/31/2025 | Medium | 1. Create review procedures2. Schedule first quarterly review (Jan 2026)3. Document process | ON TRACK | Shannon |
| POA&M-012 | Disaster recovery testing not performed | CP-4 | Schedule and conduct DR test | 12/28/2025 | High | 1. Develop test plan2. Execute test3. Document lessons learned4. Update procedures | ON TRACK | Shannon |
| POA&M-SPRS-1 | Multi-Factor Authentication not implemented for non-organizational users (contractors, vendors) | IA-8 | YubiKey tokens ($250), System Admin (8h), Security Officer (2h), Contractor training (2h) | 02/28/2026 | High | Q1 2026: Procure YubiKeys (1/15), Configure FreeIPA OTP (1/29), Enroll contractors (2/12), Complete (2/28) | ⏳ ON TRACK | System Administrator |
| POA&M-SPRS-2 | Incident Response Testing - No comprehensive tabletop exercise conducted | IR-3 | Security Officer (8h planning), Staff participation (16h total), No budget required | 06/30/2026 | Medium | Q2 2026: Plan exercise (4/1), Develop scenario (4/15), Conduct tabletop (5/15), After-action report (6/1), Complete (6/30) | ⏳ ON TRACK | Security Officer |

## Section 4: PLANNED POA&M Items

Items scheduled for future implementation:

| POA&M ID | Weakness/Deficiency | NIST Controls | Resources Required | Target Date | Priority | Milestone/Task | Status | POC |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| POA&M-013 | Wazuh Dashboard deployment for centralized visibility (Optional) | SI-4 (enhancement) | Deploy Dashboard on separate non-FIPS VM | 01/15/2026 | Low | Optional enhancement - core monitoring functional without it. Would provide improved visualization. | PLANNED | Shannon |
| POA&M-028 | VPN with MFA for remote access not deployed | AC-17, IA-2(1) | VPN software (OpenVPN/WireGuard) with MFA integration | 03/31/2026 | High | 1. Select VPN solution2. Configure with FreeIPA + MFA3. Test connections4. Document procedures5. Deploy | PLANNED | Shannon |

## Section 5: NEW POA&M Items (Added December 26, 2025)

Items identified from policy implementation review:

| POA&M ID | Weakness/Deficiency | NIST Controls | Resources Required | Target Date | Priority | Milestone/Task | Status | POC |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| POA&M-029 | Session lock not configured (15 min timeout) | AC-11 | GNOME/system settings configuration | 12/15/2025 | High | 1. Configure 15-min auto-lock on all workstations2. Test functionality3. Verify via screenshot4. Document in config baseline | NEW | Shannon |
| POA&M-030 | Audit & Accountability Policy not developed | AU-1 through AU-12 | Policy development and approval | 12/20/2025 | High | 1. Draft AU policy using existing auditd config as baseline2. Review and approve3. Update SSP4. Store in policy directory | NEW | Shannon |
| POA&M-031 | Configuration Management Policy not developed | CM-1 through CM-11 | Policy development and approval | 03/31/2026 | Medium | 1. Draft CM policy2. Document baseline configurations3. Review and approve4. Update SSP | NEW | Shannon |
| POA&M-032 | Security Awareness and Training Policy not developed | AT-1 through AT-4 | Policy development and approval | 03/31/2026 | Medium | 1. Draft AT policy2. Integrate with AUP3. Review and approve4. Update SSP | NEW | Shannon |
| POA&M-033 | Identification and Authentication Policy not developed | IA-1 through IA-11 | Policy development and approval | 03/31/2026 | Medium | 1. Draft IA policy using FreeIPA as baseline2. Document password policies3. Review and approve4. Update SSP | NEW | Shannon |
| POA&M-034 | Login banners not implemented on all systems | AC-8 | Banner configuration files | 12/15/2025 | Low | 1. Create banner text files2. Configure /etc/issue, /etc/motd, SSH banner3. Verify on all systems4. Document | NEW | Shannon |
| POA&M-035 | First annual risk assessment not conducted | RA-3 | Risk assessment execution per TCC-RA-001 | 01/31/2026 | High | 1. Use risk register template from TCC-RA-0012. Assess all CPN systems3. Document findings4. Update POA&M with identified risks | NEW | Shannon |

## POA&M Metrics

### By Status

- Completed: 16 items (57%)

- In Progress: 2 items (7%)

- On Track: 11 items (29%)

- Planned: 2 items (7%)

### By Priority

- High: 9 items (3 completed, 2 in progress, 3 on track, 1 planned)

- Medium: 10 items (13 completed as part of policy work)

- Low: 2 items

### By Target Date

- Q4 2025 (Oct-Dec): 10 items

- Q1 2026 (Jan-Mar): 8 items

- Q2 2026 (Apr-Jun): 1 item

### By Control Family

- Access Control (AC): 5 items

- Awareness & Training (AT): 3 items

- Audit & Accountability (AU): 1 item

- Security Assessment & Authorization (CA): 1 item

- Configuration Management (CM): 1 item

- Contingency Planning (CP): 2 items

- Identification & Authentication (IA): 3 items

- Incident Response (IR): 2 items (1 completed, 1 scheduled)

- Media Protection (MP): 2 items (completed)

- Physical & Environmental Protection (PE): 1 item (completed)

- Personnel Security (PS): 2 items (completed)

- Risk Assessment (RA): 4 items (3 completed, 1 new)

- System & Communications Protection (SC): 2 items

- System & Information Integrity (SI): 5 items (3 completed, 1 in progress, 1 on track)

## Completion Trend

| Date | Total Items | Completed | % Complete |
| --- | --- | --- | --- |
| 10/26/2025 | 14 | 0 | 0% |
| 10/28/2025 | 14 | 3 | 21% |
| 10/31/2025 | 14 | 3 | 21% (POA&M-014 advanced to 85%) |
| 11/02/2025 | 28 | 16 | 57% |
| Projected 12/31/2025 | 28 | 24+ | 85%+ |
| Projected 03/31/2026 | 28 | 27+ | 96%+ |
| 12/26/2025 | 31 | 16 | 52% |

## Risk Summary

### High Risk Items (Requiring Immediate Attention)

- POA&M-001: File sharing not operational (impacts AC-3, AC-6, AU-2)

- POA&M-012: Disaster recovery not tested (impacts CP-4)

- POA&M-029: Session lock not configured (impacts AC-11)

- POA&M-030: AU policy not developed (impacts AU family)

- POA&M-035: First annual risk assessment (impacts RA-3)

### Medium Risk Items

Most medium risk items are on track for completion by Q1 2026.

### Low Risk Items

- POA&M-013: Optional Wazuh Dashboard (enhancement only)

- POA&M-034: Login banners (low security impact)

## Notes

### Evidence Storage

All completed POA&M items have evidence stored in: - Policies: /backup/personnel-security/policies/ - Technical Documentation: /home/dshannon/Documents/Claude/Artifacts/ - Configuration Files: System configuration directories - Compliance Reports: /backup/compliance-scans/

### Review Schedule

- Quarterly POA&M Review: January, April, July, October

- Next Review: January 31, 2026

- POA&M Owner: Donald E. Shannon, ISSO

### Completion Criteria

POA&M items are marked complete when: 1. Technical control is implemented and operational 2. Evidence is documented and stored 3. Testing/verification is complete 4. SSP is updated to reflect implementation 5. ISSO reviews and approves completion

### Integration with SSP

This POA&M is Section 10 of the System Security Plan Version 1.4. All referenced policies and controls are documented in the SSP.

## Document Control

Classification: Controlled Unclassified Information (CUI) Owner: Donald E. Shannon, ISSO Distribution: Owner/ISSO, Authorized Auditors, C3PAO Assessors Location: /home/dshannon/Documents/Claude/Artifacts/Unified_POAM.docx Next Update: January 31, 2026 (Quarterly Review)

Revision History:

| Version | Date | Author | Description |
| --- | --- | --- | --- |
| 1.0 | 10/26/2025 | D. Shannon | Initial POA&M with 14 items |
| 1.1 | 10/28/2025 | D. Shannon | Marked POA&M-003, 008, 009 complete |
| 1.2 | 10/31/2025 | D. Shannon | POA&M-014 advanced to 85% |
| 1.3 | 11/02/2025 | D. Shannon | Unified POA&M: Marked 13 policy items complete, added 8 new items, restructured into 5 sections |
| 2.0 | 12/26/2025 | D. Shannon | Added 3 SPRS assessment gaps (POA&M-SPRS-1, SPRS-2, SPRS-3). Updated total items (28→31), On Track (8→11), priority counts. SPRS impact: -5.5 points. |
| 2.1 | 12/26/2025 | D. Shannon | System verification: Completed POA&M-001 (Samba), POA&M-010 (SSL cert), POA&M-SPRS-3 (SpamAssassin). Updated POA&M-014 to Blocked (Risk Accepted - FIPS incompatibility) |

END OF UNIFIED POA&M